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Queen’s Park Place Bridge, Oban – urgent repairs
Urgent repair works are being carried out to a crack identified in the brickwork beneath Queen’s Park Place Bridge at Oban South Bay. The works will clean, fill and seal the affected area to prevent water ingress and further deterioration. A monitoring system is also being installed to identify any future movement or changes. Works are being undertaken around low tides and are expected to be completed by 7 September. 
Roads
Capital Infrastructure Improvement surfacing works are progressing on the B8035 on Mull. The Oban team is continuing general revenue maintenance and providing support to capital works on Mull and Bute.
Japanese knotweed treatment 
Following successful specialist training of Council operatives, stem injection treatment of Japanese knotweed along the Black Lynn Burn is programmed for late September/early October. The treatment will be undertaken by the Council’s newly trained in-house operatives.
Luing and Easdale connectivity 
Work continues on the Strategic Outline Case for future transport connectivity to Luing and Easdale. Community drop-in sessions will take place at the end of September, providing an opportunity to share findings from the resident surveys, discuss identified transport challenges and gather feedback on future connectivity options. The engagement will help inform the appraisal of future vessel and infrastructure solutions for both islands.
Easdale drop in is 29th September 3:45pm til 6:45pm and Luing is 30th September from1pm til 3pm and then again from 5pm til 7pm

	
A817 Haul Road – planned resurfacing and closure

Resurfacing works are planned on the A817 between the A82 junction and the viewpoint layby as part of a £350,000 improvement scheme. The works are programmed for 10 days, from 14 to 25 September, with the road closed between 8.30am and 4.00pm on working days; no night or weekend working is planned. A signed diversion will operate via the A82, A818, C75 and A814, with agreement from BEAR Scotland for use of the A82. An embargo has also been placed on Council road works along the diversion route for the duration of the scheme to minimise further disruption.

Roads

Pre-surface dressing machine patching is being carried out at Havelock Street.

Cremator service

The recent cremator servicing has been completed successfully, with all works proceeding as planned.
	
Roads

Capital Infrastructure Improvement works are progressing on the A819 at Electric Cottage. On Islay, preparatory works are underway ahead of the deferred-set surfacing programme commencing later in September, alongside general revenue maintenance works.

A816 Millbrae landslip – works substantially complete

Repair works following the landslip at Millbrae on the A816 have now been substantially completed. Slope stabilisation and road reinstatement works have been successfully carried out and the route has reopened to traffic. The remaining works comprise final road lining and installation of additional pedestrian safety fencing, which will be completed shortly and are not expected to cause significant disruption.

Islay and Jura roads investment – new approach to island resurfacing

The next stage of the programme of road improvements on Islay and Jura will begin in mid-September, with surfacing works on the A847 north of Nerabus towards Port Charlotte. Following successful works on Jura, the Council is using a modern deferred-set ‘cold mix’ material which can be manufactured in bulk, transported to the islands by barge and used over a longer period. For the Islay works, material will be delivered directly to Bruichladdich, allowing more surfacing to be completed efficiently while reducing reliance on ferry capacity and the need to keep conventional material hot during transport. The A847 will operate scheduled closure and opening periods during the works, with arrangements in place to maintain bus and school transport services and an alternative route available via Kilchiaran and Portnahaven. Subject to progress, weather and material availability, further surfacing is also planned on the B8016 at Leorin.

Port Askaig ferry slip – works progressing well

Repair works at Port Askaig ferry slip are progressing well, with replacement wear strips and associated concrete repairs now substantially advanced. The remaining resurfacing works are programmed for next week and, subject to weather and site conditions, are expected to be completed by Thursday. The project remains on programme, with ferry operations continuing to be accommodated throughout the works and the slipway remaining available for use over the weekend.



	
Ardbeg Seawall, Rothesay – works complete

Improvement works to the seawall on the A844 at Ardbeg Road have now been completed. The scheme has included new concrete slabs and edge beams tied into the existing coastal defences, repairs to the masonry seawall, and new rock armour and toe protection to provide greater resilience against wave action, scour and coastal erosion. Existing drainage issues at the northern end of the site have also been addressed, while affected footways have been resurfaced and new pedestrian handrails, bollards and chains installed. A small number of minor defects identified following completion will be addressed by the contractor during the 52-week defects correction period.

Roads

Capital Infrastructure Improvement surfacing works are progressing on Auchamore Road, with preparatory works also underway ahead of planned surfacing at Alexander Street.
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