## Sheet1
Appendix 1 | Dates are calender years split into quarters for the purpose of this high level plan
Provisional Dates for tasks - will be subject to change as the project evolves | 2021 | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027
Issue date - May 2022 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Task
Initial discussions with CMAL to agree a way forward following the HB meeting on 2 December 2021 | bar: 2021 Q4
Meeting with CMAL and NLB | bar: 2021 Q4
Meeting with Oban Bay Management Group seeking endorsement of ABC becoming the SHA | bar: 2022 Q1
Extend DP contract to provide project support | bar: 2022 Q1
Workshop with internal staff, CMAL, CalMac and DP to scope out the programme | bar: 2021 Q4
formally set up a Harbour Management Co-Ordination Group | bar: 2022 Q3
Model for fees and charges 'v' costs - initial build and annual review | bar: 2022 Q3 to 2022 Q4; 2023 Q3; 2024 Q3; 2025 Q3; 2026 Q3; 2027 Q3
Fees and charges to Council | bar: 2022 Q1; 2023 Q1; 2024 Q1; 2025 Q1; 2026 Q1; 2027 Q1
Determine the limits for a SHA - further workshop sessions with DP, CMAL, CalMac, NLB | bar: 2022 Q1
Navigational Risk Assessment and the Pilotage Assessment | bar: 2022 Q2 to 2022 Q3
NLB agreement on buoyage maintenance TBC | bar: 2022 Q2
Carry our Navigational Risk Assessments | bar: 2022 Q2 to 2022 Q3
Draft provision for the HRO/HEO- General Directions and Powers - | bar: 2022 Q1 to 2022 Q3
Set out draft operating hours - consult with the major stakeholders. Include provision for out of hours | bar: 2022 Q1
informal discussion with TS regarding limits and provisions for the HRO/HEO (series of mtgs) | bar: 2022 Q1 to 2022 Q2
Commence Pre Order consultation with statutory consultees (list as per requirements of TS and Harbour legislation) | bar: 2022 Q2
Commence Pre Order consultation for limits and provisions for the HRO/HEO through a 'Harbour User Group' consisting of all known Oban bay users, including island CCs who have ferry connections with Oban | bar: 2022 Q3
Assessment of representations and any adjustments to drafts as appropriate | bar: 2022 Q3 to 2022 Q4
Scheduled Hartbour Board Meetings - update on progress | bar: 2022 Q1; 2022 Q3; 2023 Q1; 2023 Q3; 2024 Q1; 2024 Q3; 2025 Q1; 2025 Q3; 2026 Q1; 2026 Q3; 2027 Q1; 2027 Q3
Special Meeting of the HB should there be a requirement
Pre submission checks with TS - prior to submitting the Draft Order request to TS | bar: 2022 Q4
Order submission to TS | bar: 2022 Q4 to 2023 Q1
Transport Scotland application assessment, advertise and deal with any representations (TS estimate 4 - 8 months) | bar: 2022 Q4 to 2023 Q2
Scope out and determine supporting measures required for a SHA, detailed below:
- VTS | bar: 2022 Q1
- Bathometric Survey | bar: 2022 Q1
- Operational Vessel/work boat | bar: 2022 Q1
- It System for payments and dues | bar: 2022 Q4
- Marks and Buoys | bar: 2022 Q2
- Operating Manual SMS | bar: 2022 Q1 to 2022 Q3
- Web Site and communications strategy | bar: 2022 Q2
- Oil Spill Response Plan | bar: 2022 Q1
- Border Force/Immigration Plan HMRC bespoke model. Contact with National Frontier Approvals Unit – Similar or the same as Campbeltown | bar: 2022 Q1
- VHS provision and licence | bar: 2022 Q1
Design staffing structure, work patterns and cover | bar: 2022 Q1 to 2022 Q2
Staff Recruitment | bar: 2022 Q4 to 2023 Q1
Staff Training | bar: 2022 Q4 to 2023 Q2
Implement supporting measures detailed below
- VTS | bar: 2023 Q2
- Bathometric Survey | bar: 2023 Q2
- Operational Vessel/work boat | bar: 2023 Q2
- It System for payments and dues | bar: 2023 Q1
- Marks and Buoys | bar: 2023 Q2
- Operating Manual SMS | bar: 2023 Q2
- Web Site and communications strategy | bar: 2023 Q2
- Oil Spill Response Plan | bar: 2023 Q2
- Border Force/Immigration Plan HMRC bespoke model. Contact with National Frontier Approvals Unit – Similar or the same as Campbeltown | bar: 2023 Q2
- VHS provision and licence | bar: 2023 Q2
Systems Testing | bar: 2023 Q2
Dry Run prior to full implementation | bar: 2023 Q3
Go Live date ABC become SHA - assuming HRO runs smoothly - no gaurantee as this is out of the control of ABC | bar: 2023 Q3
Monitoring, adjustment and bedding of the new SHA in line with the Council's PMSC | bar: 2023 Q4 to 2024 Q3
Operation as SHA, audit, review and adjustment as per the Council's exsisting PMSC approach | bar: 2024 Q4 to 2027 Q4
Review of costs 'v' fees and charges | bar: 2022 Q4
Formalise and change the scope / TOR of OBMG to continue past the transition – meetings / user groups / Safety Forum etc. TBC | bar: 2022 Q4
Risk register | bar: 2022 Q2
|  | Key |  | to be commenced
complete
on going/partially complete
Off Track